**Timeline to Fully Implement Pathway Models**

***Fully Implement = IB World School, Asia Society International School, Ohio STEM Network***

|  |  |  |
| --- | --- | --- |
| **Society** | **Discovery** | **Creativity** |
| **Roxboro E - IB** | **Boulevard STEM** | **Noble-IB Arts** |
| * **Investigate 9/10-4/11**
* **Candidate Status 9/11-7/14**
* **World School 7/14**
 | * **Investigate 9/10-6/11**
* **Implement PAST STEM Inquiry Model 9/11-6/14**
* **Fully Implemented Ohio STEM Academy 6/14**
 | * **Investigate 9/11-4/12**
* **Candidate Status 4/12-7/15**
* **World School 7/15**
 |
| **Roxboro M - IB** | **Gearity PD School** | **Canterbury –IB Arts** |
| * **Investigate 9/11-4/12**
* **Candidate Status 9/12-7/15**
* **World School 7/15**
 | * **Investigate 9/11-6/12**
* **Implement PAST STEM Inquiry Model 9/12-6/15**
* **Fully Implemented Ohio STEM Academy 6/15**
 | * **Investigate 9/12-4/13**
* **Candidate Status 4/13-7/16**
* **World School 7/16**
 |
| **Fairfax** | **Monticello New Tech STEM** | **Wiley –IB Arts** |
| * **Investigate 9/12-4/13**
* **Candidate Status 9/13-7/16**
* **World School 7/16**
 | * **Investigate 9/11-6/12**
* **Implement New Tech Model (design year 9/12-6/13)**
* **Implementation phase 2: 9/13-15**
* **Fully implemented 9/15**
 | * **Investigate 9/12-4/13**
* **Candidate Status 4/13-7/16**
* **World School 7/16**
 |
| **Oxford** | **Legacy New Tech STEM** | **Mosaic** |
| * **Investigate 9/12-4/13**
* **Candidate Status 9/13-7/16**
* **World School 7/16**
 | * **Investigate 9/10-6/11**
* **Implement New Tech Model (design year 9/11-6/12)**
* **Implementation phase 2: 9/12-14**
* **Fully implemented 9/14**
 | * **Investigate/Design phase 9/11-12**
* **Implementation 9/12-14**

**(need to develop an inquiry instructional framework to align with IB ARTS)** |
| **Renaissance (International Network Schools)** |  |  |
| * **Design Phase 9/11-12**
* **Implementation 9/12-6/14**
* **International Network School Designation 7/14**
 |  |  |