**Timeline to Fully Implement Pathway Models**

***Fully Implement = IB World School, Asia Society International School, Ohio STEM Network***

|  |  |  |
| --- | --- | --- |
| **Society** | **Discovery** | **Creativity** |
| **Roxboro E - IB** | **Boulevard STEM** | **Noble-IB Arts** |
| * **Investigate 9/10-4/11** * **Candidate Status 9/11-7/14** * **World School 7/14** | * **Investigate 9/10-6/11** * **Implement PAST STEM Inquiry Model 9/11-6/14** * **Fully Implemented Ohio STEM Academy 6/14** | * **Investigate 9/11-4/12** * **Candidate Status 4/12-7/15** * **World School 7/15** |
| **Roxboro M - IB** | **Gearity PD School** | **Canterbury –IB Arts** |
| * **Investigate 9/11-4/12** * **Candidate Status 9/12-7/15** * **World School 7/15** | * **Investigate 9/11-6/12** * **Implement PAST STEM Inquiry Model 9/12-6/15** * **Fully Implemented Ohio STEM Academy 6/15** | * **Investigate 9/12-4/13** * **Candidate Status 4/13-7/16** * **World School 7/16** |
| **Fairfax** | **Monticello New Tech STEM** | **Wiley –IB Arts** |
| * **Investigate 9/12-4/13** * **Candidate Status 9/13-7/16** * **World School 7/16** | * **Investigate 9/11-6/12** * **Implement New Tech Model (design year 9/12-6/13)** * **Implementation phase 2: 9/13-15** * **Fully implemented 9/15** | * **Investigate 9/12-4/13** * **Candidate Status 4/13-7/16** * **World School 7/16** |
| **Oxford** | **Legacy New Tech STEM** | **Mosaic** |
| * **Investigate 9/12-4/13** * **Candidate Status 9/13-7/16** * **World School 7/16** | * **Investigate 9/10-6/11** * **Implement New Tech Model (design year 9/11-6/12)** * **Implementation phase 2: 9/12-14** * **Fully implemented 9/14** | * **Investigate/Design phase 9/11-12** * **Implementation 9/12-14**   **(need to develop an inquiry instructional framework to align with IB ARTS)** |
| **Renaissance (International Network Schools)** |  |  |
| * **Design Phase 9/11-12** * **Implementation 9/12-6/14** * **International Network School Designation 7/14** |  |  |